## Company Definition
BUDGET
Product | Price | Quantity | Maintenance/unit | Annual cost | Type | Time window | Amortization | Role | Quantity | Yearly gross salary | Yearly salary cost | Total
Microsoft Windows 11 | 0 | 2 | 0 | 0 | Amortization | 4 | 0 | Team Leader | 1 | 45000 | 59490 | 59490
Microsoft Office 365 | 10 | 2 | 0 | 240 | Subscription | Monthly | 0 | Data Engineer | 1 | 35000 | 46270 | 46270
Microsoft Project 2016 | 59.9 | 1 | 0 | 14.975 | Amortization | 4 | 4.9912 | Junior Developer | 1 | 24000 | 31728 | 31728
Claude Code | 20 | 1 | 0 | 240 | Subscription | Monthly | 0 | Project Leader | 1 | 53300 | 70462.6 | 70462.6
PyCharm Pro | 13.19 | 1 | 0 | 158.28 | Subscription | Monthly | 0 | Total |  |  |  | 207950.6
MongoDB Atlas | 0 | 1 | 0 | 0 | Subscription | 4 | 0
Vercel | 0 | 1 | 0 | 0 | Subscription | 4 | 0 | Role | Total | Prod (%) | Direct cost | CI (%) | Indirect cost | Concept | Cost
GitHub | 0 | 1 | 0 | 0 | Subscription | 4 | 0 | Team Leader | 59490 | 65% | 38668.5 | 35% | 20821.5 | Total direct costs | 122959.22
Docker Desktop | 0 | 1 | 0 | 0 | Amortization | 4 | 0 | Data Engineer | 46270 | 90% | 41643 | 10% | 4627 | Total indirect costs | 107184.135
Google AI Studio | 0 | 1 | 0 | 0 | Subscription | 4 | 0 | Junior Developer | 31728 | 90% | 28555.2 | 10% | 3172.8 | Total costs | 230143.355
HP ENVY 17-da0000ns (Includes Windows License) | 3198 | 2 | 100 | 849.5 | Amortization | 4 | 283.1384 | Project Leader | 70462.6 | 20% | 14092.52 | 80% | 56370.08 | Target benefits (25%) | 57535.8388
Total |  |  |  | 1502.755 |  |  |  | Total |  |  | 122959.22 |  | 84991.38 | Billing needs | 287679.1938
[14 empty] | Billing based on productive hours | 287679.1938
[8 empty] | Role | Prod. Hours/yr | Price/hour | Billing | Price/hour (w/o benefits) |  | Total costs-billing margin | 0
Service | Monthly cost | Anual cost |  |  |  |  | 1750 | Team Leader | 1137.5 | 71.3835 | 81198.6853 | 57.1068
Office cleaning | 120 | 1440 |  |  |  |  | 1750 | Data Engineer | 1575 | 61.9406 | 97556.4488 | 49.5525
Office rent | 650 | 7800 |  |  |  |  | 1750 | Junior Developer | 1575 | 51.5535 | 81196.6988 | 41.2428
Office supplies | 60 | 720 |  |  |  |  | 1750 | Project Leader | 350 | 79.221 | 27727.3608 | 63.3768
Electricity & climate control | 95 | 1140 | [5 empty] | Total | 4637.5 |  | 287679.1938
Water expenses | 20 | 240
Waste tax | 0 | 150
Transport | 200 | 2400 | [8 empty] | Overhead | 23.1125
Audits | 125 | 1500
Fiber Internet | 70 | 840
Accounting and payroll services | 160 | 1920
Insurance | 0 | 500
Hardware maintenance | 25 | 300
Security and alarm system | 45 | 540
Communication costs | 100 | 1200
Total | 1670 | 20690

## Detailed Budget
I1 | I2 | I3 | Description | Quantity | Units | Price | Subtotal | Total | Task | Cost
01 |  |  | Sprint 1: Analysis and planning | 106 | Hours |  |  | 5421.7791 | Sprint 1: Analysis and planning | 6777.2239
| 001 |  | Project planning | 8 | Hours |  | 456.8541 |  | Sprint 2: System design | 5309.7035
|  | 01 | Team Leader |  | Hours | 57.1068 |  |  | Sprint 3: Backend & pipeline development | 4095.7911
| 002 |  | Project budgeting | 8 | Hours |  | 456.8541 |  | Sprint 4: Full NLP pipeline implementation | 4622.4774
|  | 01 | Team Leader |  | Hours | 57.1068 |  |  | Sprint 5: Data visualizations and web application aspects | 3918.0629
| 003 |  | Literature research (topic modeling, BERT, classification…) | 10 | Hours |  | 571.0677 |  | Sprint 6: Final documentation & product refinements | 2216.7988
|  | 01 | Team Leader |  | Hours | 57.1068 |  |  | Fortnightly meetings | 4425.7291
| 004 |  | ActEU paper research | 10 | Hours |  | 571.0677 |  | Subtotal | 31365.7867
|  | 01 | Team Leader |  | Hours | 57.1068 |  |  | VAT (21%) | 6586.8152
| 005 |  | Similar theses research | 10 | Hours |  | 571.0677 |  | Total (+ VAT) | 37952.6019
|  | 01 | Team Leader |  | Hours | 57.1068
| 006 |  | Dataset understanding (format, metadata…) | 8 | Hours |  | 396.4199
|  | 01 | Data Engineer |  | Hours | 49.5525
| 007 |  | Research of alternatives | 8 | Hours |  | 329.9421
|  | 01 | Junior Developer |  | Hours | 41.2428
| 008 |  | Use case developing | 8 | Hours |  | 329.9421
|  | 01 | Junior Developer |  | Hours | 41.2428
| 009 |  | Overall technological decisions | 8 | Hours |  | 456.8541
|  | 01 | Team Leader |  | Hours | 57.1068
| 010 |  | Project requirements | 8 | Hours |  | 456.8541
|  | 01 | Team Leader |  | Hours | 57.1068
| 011 |  | Interface mock-ups | 8 | Hours |  | 329.9421
|  | 01 | Junior Developer |  | Hours | 41.2428
| 012 |  | Documentation (Chapters 2 & 4) | 12 | Hours |  | 494.9132
|  | 01 | Junior Developer |  | Hours | 41.2428
02 |  |  | Sprint 2: System design | 84 | Hours |  |  | 4247.7628
| 001 |  | Data processing pipeline design | 8 | Hours |  | 396.4199
|  | 01 | Data Engineer |  | Hours | 49.5525
| 002 |  | Web system architecture design | 10 | Hours |  | 571.0677
|  | 01 | Team Leader |  | Hours | 57.1068
| 003 |  | Testing strategy | 12 | Hours |  | 685.2812
| 004 | 01 | Team Leader |  | Hours | 57.1068
|  |  | Database design | 8 | Hours |  | 396.4199
| 005 | 01 | Data Engineer |  | Hours | 49.5525
|  |  | Class design | 10 | Hours |  | 713.8346
| 006 | 01 | Team Leader |  | Hours | 71.3835
| 007 | 01 | Tech stack sandboxing | 6 | Hours |  | 247.4566
|  |  | Junior Developer |  | Hours | 41.2428
| 008 | 01 | Documentation (Chapter 5) | 20 | Hours |  | 824.8554
|  |  | Junior Developer |  | Hours | 41.2428
| 009 | 01 | Github setup | 10 | Hours |  | 412.4277
|  |  | Junior Developer |  | Hours | 41.2428
03 |  |  | Sprint 3: Backend & pipeline development | 73 | Hours |  |  | 3276.6329
| 001 |  | Main backend functionalities | 8 | Hours |  | 329.9421
|  | 01 | Junior Developer |  | Hours | 41.2428
| 002 |  | Database deployment & faceted search functionalities | 8 | Hours |  | 396.4199
|  | 01 | Data Engineer |  | Hours | 49.5525
| 003 |  | Document retrieval based on user query | 10 | Hours |  | 495.5248
|  | 01 | Data Engineer |  | Hours | 49.5525
| 004 |  | Unit testing | 8 | Hours |  | 329.9421
|  | 01 | Junior Developer |  | Hours | 41.2428
| 005 |  | Initial topic modeling mock with specific cases | 14 | Hours |  | 693.7347
|  | 01 | Data Engineer |  | Hours | 49.5525
| 006 | 01 | Documentation (Chapters 3 & 6) | 25 | Hours |  | 1031.0692
|  |  | Junior Developer |  | Hours | 41.2428
04 |  |  | Sprint 4: Full NLP pipeline implementation | 81 | Hours |  |  | 3697.9819
| 001 |  | LLM reconciliation of specific use case topics | 6 | Hours |  | 297.3149
|  | 01 | Data Engineer |  | Hours | 49.5525
| 002 |  | Topic generation for any query | 12 |  |  | 594.6298
|  | 01 | Data Engineer |  |  | 49.5525
| 003 |  | Unit testing | 8 |  |  | 329.9421
|  | 01 | Junior Developer |  |  | 41.2428
| 004 |  | Human topic confirmation functionality | 4 |  |  | 164.9711
|  | 01 | Junior Developer |  |  | 41.2428
| 005 |  | Classificator training based on validated topics functionality | 10 |  |  | 495.5248
|  | 01 | Data Engineer |  |  | 49.5525
| 006 |  | Dataset labeling through classificator functionality | 15 |  |  | 743.2872
|  | 01 | Data Engineer |  |  | 49.5525
| 007 |  | Unit testing | 10 |  |  | 412.4277
|  | 01 | Junior Developer |  |  | 41.2428
| 008 |  | Documentation (Chapters 8, 9) | 16 |  |  | 659.8843
|  | 01 | Junior Developer |  |  | 41.2428
05 |  |  | Sprint 5: Data visualizations and web application aspects | 76 |  |  |  | 3134.4503
| 001 |  | Narrative trend visualizations | 8 |  |  | 329.9421
|  | 01 | Junior Developer |  |  | 41.2428
| 002 |  | WAF configuration & other security aspects | 10 |  |  | 412.4277
|  | 01 | Junior Developer |  |  | 41.2428
| 003 |  | Web application refinements | 15 |  |  | 618.6415
|  | 01 | Junior Developer |  |  | 41.2428
| 004 |  | Usability tests | 10 |  |  | 412.4277
|  | 01 | Junior Developer |  |  | 41.2428
| 005 |  | Deployment | 8 |  |  | 329.9421
|  | 01 | Junior Developer |  |  | 41.2428
| 006 |  | Documentation (Chapters 9, 10 & 11) | 25 |  |  | 1031.0692
|  | 01 | Junior Developer |  |  | 41.2428
06 |  |  | Sprint 6: Final documentation & product refinements | 43 |  |  |  | 1773.439
| 001 |  | Documentation (Chapters 1, 12 & 13) | 25 |  |  | 1031.0692
|  | 01 | Junior Developer |  |  | 41.2428
| 002 |  | Frontend refinements | 10 |  |  | 412.4277
|  | 01 | Junior Developer |  |  | 41.2428
| 003 |  | Usability tests | 8 |  |  | 329.9421
|  | 01 | Junior Developer |  |  | 41.2428
07 |  |  | Fortnightly meeting | 8 |  |  |  | 3540.5833
| 001 |  | Meeting 1 | 1 |  |  | 98.3495
|  | 01 | Junior Developer |  |  | 41.2428
|  | 02 | Project Leader |  |  | 57.1068
| 002 |  | Meeting 2 | 2 |  |  | 196.6991
|  | 03 | Junior Developer |  |  | 41.2428
|  | 04 | Project Leader |  |  | 57.1068
| 003 |  | Meeting 3 | 3 |  |  | 295.0486
|  | 05 | Junior Developer |  |  | 41.2428
|  | 06 | Project Leader |  |  | 57.1068
| 004 |  | Meeting 4 | 4 |  |  | 393.3981
|  | 07 | Junior Developer |  |  | 41.2428
|  | 08 | Project Leader |  |  | 57.1068
| 005 |  | Meeting 5 | 5 |  |  | 491.7477
|  | 09 | Junior Developer |  |  | 41.2428
|  | 10 | Project Leader |  |  | 57.1068
| 006 |  | Meeting 6 | 6 |  |  | 590.0972
|  | 11 | Junior Developer |  |  | 41.2428
|  | 12 | Project Leader |  |  | 57.1068
| 007 |  | Meeting 7 | 7 |  |  | 688.4467
|  | 13 | Junior Developer |  |  | 41.2428
|  | 14 | Project Leader |  |  | 57.1068
| 008 |  | Meeting 8 | 8 |  |  | 786.7963
|  | 15 | Junior Developer |  |  | 41.2428
|  | 16 | Project Leader |  |  | 57.1068
Total | [7 empty] | 25092.6293